ACUMENUS

ZEPHYRUS  ·  HOSPITAL OPERATIONS INTELLIGENCE

Hummingbird

Consolidated Implementation Plan

The native mobile companion to Zephyrus — Android · iOS · shared Kotlin Multiplatform core

ACUM-ENG-HMB-001

Sanjay M. Udoshi, MD

Founder, Acumenus, Inc.

Planning v1  ·  June 26, 2026

CONFIDENTIAL

© 2026 Acumenus, Inc. All rights reserved.

Native mobile companion to Zephyrus. The web app answers “what is happening across the hospital, and why?” on wall displays and workstations. This document is the single authoritative plan for the phone: it states the cross-cutting invariants once (Part II), sequences the work as six self-contained phases (Part III), and backs both with a full parity matrix and reference appendices (Part IV).

Status Planning v1 · 2026-06-26. Bounded by the locked authentication rules in .claude/rules/auth-system.md — all backend work described here is strictly additive. Deep-dive docs (00–07) and the seven-stream code audit (research/) provide field-level detail.

## Contents

Part I — Strategy & Context	3

1.  Executive summary	3

2.  Why a companion, not a port	4

3.  What the audit found	4

4.  Personas — all levels of the delivery system	5

Part II — The Invariants	6

5.  Architecture	6

6.  Real-time & offline model	6

7.  The Mobile BFF & auth model	7

8.  Design-system parity	8

9.  Earned-urgency notifications	8

10.  Security & HIPAA gates	8

11.  The shared core every worker gets	9

Part III — The Phased Plan	10

Phase 0 — Foundation	10

Phase 1 — Frontline workers & bed flow	11

Phase 2 — Decisions & the OR board	12

Phase 3 — Awareness breadth	13

Phase 4 — Net-new backend features	13

Phase 5 — Hardening & GA	14

Part IV — Reference	16

Appendix A — Full feature-parity matrix	16

Appendix B — Backend change log	18

Appendix C — Risk register	18

Appendix D — Team & timeline	18

Appendix E — Program definition of done	19

Document map	19

PART I

# Strategy & Context

## 1. Executive summary

Hummingbird is the glance-and-act surface of Zephyrus. The web app answers “what is happening across the hospital, and why?” on wall displays and workstations. Hummingbird answers a sharper question for a worker mid-shift, in a hand, in three seconds:

“What needs me, right now — and can I do it in two taps?”

One native app per platform adapts its home, its unified “For You” action queue, and its notification defaults to the signed-in worker — from the transporter moving a patient to the CMO glancing at house status between meetings.

The headline decisions

| Decision | Choice | Rationale |
| --- | --- | --- |
| UI | Native per platform (Compose + SwiftUI) | Glanceability and feel are the product; native widgets, Live Activities, Critical Alerts |
| Shared code | KMP domain + data core, bridged via SKIE | Clinical/status logic is “defensible” — it must not drift between two codebases |
| Backend access | A versioned mobile BFF (/api/mobile/v1/*) | The web /api is chatty, inconsistently authed, PHI-rich |
| Auth | Sanctum tokens (+ OIDC/PKCE path), additive | Move off session cookies without touching the locked flow |
| Real-time | Push-first, websocket-when-foregrounded, poll fallback | Battery + correctness; never hold a background socket |
| Offline | Offline-aware (cache reads, queue non-critical writes) | Spotty hospital Wi-Fi; block safety-critical writes offline |
| Notifications | Server-side four-tier “earned-urgency” router | Alarm fatigue is a clinical-safety failure, not a UX nit |
| Design | One DTCG token source → Compose + SwiftUI + CSS | One design system, three platforms, zero drift |

The plan in one picture

P0 Foundation ###### auth · push · BFF · tokens · RBAC · assignment model P1 Frontline ###### Transport · EVS · RTDC beds/barriers · For-You · notif v1 P2 Decisions ######## Ops approvals · Command/Brief · OR board · huddles P3 Awareness ###### ED signals · Staffing · transfers · watch/widgets P4 Net-new ######## PI/PDSA · ED actions · integration health P5 Hardening/GA ###### security + clinical-safety review · perf · rollout

~9–12 months to GA for a focused team; usable internal pilots from end of P1. Phases P1–P2 can overlap once the BFF pattern is set.

The sequencing logic (why this order)

Three platform gaps gate everything, so they come first (P0). Then we build on live data with low backend risk for fast value — RTDC, Ops approvals, Transport, EVS all run on existing endpoints (P1–P2). Features that require net-new backend (ED clinician actions, Process Improvement) are deferred (P4) because their web surfaces are mock/stub today; we still ship their glanceable signals earlier where the data already exists (P3). Hardening and the safety/security gates that GA legally depends on close the program (P5).

## 2. Why a companion, not a port

Zephyrus is a dense, instrument-rich operations bridge built for multi-panel study. Most of that does not belong on a phone under time pressure. Every web capability is triaged against the glance-and-act question into one treatment:

| Flag | Meaning | Mobile treatment |
| --- | --- | --- |
| GLANCE | Read at a glance; situational awareness | Home tiles, widgets, Live Activities |
| ACT | A worker would act on it from a phone | First-class flows + notification actions |
| NOTIFY | A discrete event worth a push | The earned-urgency taxonomy |
| WEB | Too analytical/dense for phone | Deep-link to web; not rebuilt |

Rule of thumb If a task needs more than ~3 visible panels, a keyboard, or sustained study (utilization analytics, process mining, simulation authoring, blueprint modeling, admin), it stays on the web and Hummingbird offers a one-tap deep link.

This plan honors the Zephyrus canon on mobile: Rigorous · Composed · Defensible; earned urgency (color and pushes are rationed); status never by color alone; dark-default, tabular-nums, gold focus; replace the EHR, don’t reskin it. It is not a shrunk dashboard, not a consumer health app, and never an alarm-fatigue pager.

## 3. What the audit found

A seven-stream parallel audit (95 models, ~106 API endpoints, all four workflows + supporting domains + platform) produced five findings that shape the entire sequence.

Per-domain readiness (this drives phasing)

| Domain | Data model | API contract | Live data | Real-time | Verdict |
| --- | --- | --- | --- | --- | --- |
| RTDC | ✓ rich | ✓ /api/rtdc/* | ✓ event-sourced | ✓ Reverb WS | Flagship — build first |
| Ops / AI approvals | ✓ ops.* | ✓ /api/ops/* | ✓ production-grade | — | Reuse endpoints verbatim |
| Transport / EVS / Staffing | ✓ | ✓ endpoints | ✓ event logs | — | Textbook mobile workers |
| Perioperative | ✓ rich | ✓ /api/cases,blocks | △ mostly mock UI | ✗ local timers | Ready data, no surface |
| Command Center | ✓ | ✓ /api/command-center/* | ✓ | — | Strain index + Exec Brief |
| Emergency Dept | △ 2 tables | ✗ 0 ED endpoints | △ via Command/Analytics | ✗ | Glance now, act later (NEW) |
| Process Improvement | △ models only | ✗ stub | ✗ empty stubs | ✗ | Net-new backend |

The three platform gaps that gate everything

- No mobile auth. Session-cookie only; Sanctum is installed but dormant (User lacks HasApiTokens, zero auth:sanctum routes). OIDC/Authentik exists but also lands a web session. → token auth is net-new (additive).

- No push infrastructure. Zero APNs/FCM, no device registry, no notifier. Only Reverb websockets (foreground) + one demo SSE. → push is net-new.

- Inconsistent API auth & shape. Several operational endpoints (cases, blocks, rooms, providers, analytics, improvement/*) carry no `auth` middleware; no uniform envelope; PHI interleaved with operational data. → a BFF is required.

Full detail: research/ (02-rtdc, 03-perioperative, 04-improvement-and-ops, 05-platform-auth-realtime-design, 06-supporting-domains-and-api, 01-emergency-department, 07-mobile-best-practices).

## 4. Personas — “all levels of the delivery system”

One app, role-adaptive home. Zephyrus treats its audience as one product switched by a workflow_preference (a preference, not a hard permission); Hummingbird honors that and extends down to the frontline mobile worker the web under-serves.

| # | Persona | Altitude | Phase | Home emphasis |
| --- | --- | --- | --- | --- |
| P1 | Transporter / Porter | Frontline worker | 1 | My trips + available jobs |
| P2 | EVS Technician | Frontline worker | 1 | My bed-turns + next dirty bed |
| P3 | Bedside / Charge Nurse | Frontline unit | 1–2 | My unit: census, barriers, incoming |
| P4 | OR Circulating / Charge Nurse | Frontline OR | 2 | Live room board + my cases |
| P5 | Nursing Supervisor / Bed Manager | Ops leader | 1 | House bed-need + pending requests |
| P6 | Patient-Flow / Capacity Lead | Ops leader | 2 | Capacity vs demand + approvals inbox |
| P7 | Perioperative Manager | Ops leader | 2–3 | OR day at a glance |
| P8 | PI / Quality Lead | Ops leader | 4 | My PDSA cycles + barrier trends |
| P9 | Executive (CMO/COO/CNO) | Executive | 2 | One quiet strain index + Brief |
| P10 | Staffing Coordinator | Ops leader | 3 | Open requests + below-safe units |

The altitude model

How “earned urgency” expresses per level: a frontline worker’s home is a task list; a unit’s home is my unit / my cases; an ops leader’s home is the house / my domain; an executive’s home is a single strain index that stays quiet until it shouldn’t. Full per-persona journeys: reference/02-core-functionality-by-role.md.

PART II

# The Invariants

These decisions are constant across all phases. They are stated once here; each phase references them rather than re-deciding.

## 5. Architecture

Native UI per platform over a shared KMP domain/data core. This single decision must be made now — committing to shared Kotlin logic puts Kotlin/Native in the iOS build, and deciding late forces an expensive re-architecture. If the org rejects KMP, the floor is two fully-separate apps bound by the API contract + a shared conformance test spec.

PRESENTATION (native) Android: Compose + ViewModel (MVVM-UDF; MVI for dense boards) iOS: SwiftUI + @Observable (TCA only for true state machines) → widgets · Live Activities/Dynamic Island · Watch/Wear SHARED (KMP) domain models · use-cases · status rules · urgency scoring · validation data repositories · Ktor BFF client · SQLDelight cache · outbox · sync engine · Reverb/Pusher realtime · token store tokens generated from DTCG (see §8) PLATFORM (expect/actual) Keychain/Keystore · biometrics · APNs/FCM · BGTasks/WorkManager

- Android: Compose (Material3 themed to Zephyrus tokens, not default Material), Hilt, Coroutines/Flow, Ktor, SQLDelight, DataStore, WorkManager, FCM, Glance widgets, Wear.

- iOS: SwiftUI + Observation, Swift Concurrency, Ktor-via-shared (or URLSession actual), SQLDelight, Keychain, BGTaskScheduler, APNs (+ Critical Alerts, ActivityKit), WidgetKit, watchOS. SKIE generates idiomatic Swift over the KMP module.

- Feature modules are vertical slices depending only on shared/domain + shared/data + core-ui. The For-You feature composes every domain through one ForYouFeed use-case in shared/domain — the single home of the earned-urgency ranking.

Module/repo structure and the full stack rationale: reference/03-architecture.md.

## 6. Real-time & offline model

Three-mode real-time (mirrors the web’s Reverb posture and extends it for battery):

| App state | Transport | Behavior |
| --- | --- | --- |
| Foreground, screen on | Reverb WS (Pusher protocol) | Live tiles; re-snapshot all visible queries on (re)connect — Reverb does not replay |
| Background / locked | Push (APNs/FCM) | Silent push → WorkManager/BGTask delta-sync; visible push for NOTIFY events |
| No connectivity | Poll on resume + cache | Stale badge; reconcile outbox |

We never hold a websocket in the background. Public WS channels are PHI-free (counts/ids only); any future PHI-on-wire needs PrivateChannel + token channel auth.

Offline-aware, not offline-first

- Reads: cache-then-network; emit cached immediately with an as-of timestamp, refresh, re-emit; on failure keep cache + show a stale badge (never a blank screen).

- Non-critical writes (acknowledge, claim routine job, routine status): optimistic local apply + outbox; flush on reconnect.

- Safety-critical writes (approve an action, place a bed, complete an isolation bed-turn, advance a case past a clinical gate): require connectivity; if offline, the action is disabled with an explicit reason — never silently queued.

- Conflicts: last-write-wins + field-merge + server version/ETag; 409 surfaces “changed since you loaded — review,” never a blind overwrite. No CRDTs.

## 7. The Mobile BFF & auth model

*A versioned BFF (`/api/mobile/v1/) is the only surface the apps talk to.** It reuses existing models/services and **delegates all mutations** to the existing lifecycle services (OperationalActionLifecycleService, the RTDC engine, the Transport/EVS/Staffing *OperationsService`s) — it reshapes, it does not re-implement.

BFF rules

- One screen → one call where practical; uniform envelope { data, meta:{as_of,stale,version}, links:{web} }.

- `auth:sanctum` on everything; role-scoped and PHI-minimized (tokenized/initials in lists; full PHI only on an explicit authorized detail call, never in lists or notifications).

- ETag/cursor/updated_since for concurrency and delta sync.

Auth (additive — never touches the locked flow)

Add HasApiTokens to User; issue Sanctum personal access tokens with role-matched abilities; provide an OIDC+PKCE path reusing Authentik for SSO orgs. The token endpoints honor `must_change_password` by returning a scoped change-challenge (the temp-password/Resend/superuser flow is preserved verbatim). Tokens live in Keychain/Keystore gated by biometrics; short-lived access + rotating refresh; idle auto-lock; server-side revoke for remote wipe.

RBAC

Reads stay broad (house status is for everyone at their altitude, PHI-gated); writes get Laravel Policies so a device can only act within role/assignment (only the assigned transporter progresses a trip; only an authorized approver decides an action). This requires the assignment model (Phase 0). The contract: api-contract/hummingbird-bff.v1.yaml (OpenAPI 3.1, validated). Full spec: reference/04-backend-requirements.md.

## 8. Design-system parity

One DTCG token source → three platforms, verified non-divergent in CI. The web keeps its Tailwind setup; design-tokens/tokens.json generates Compose + SwiftUI equivalents via Style Dictionary and a CI job diffs resolved values against tailwind.config.js + .impeccable/design.json — a mismatch fails the build.

The tokens encode the Zephyrus canon: the Two-System Rule (operational blue/slate #2563EB/#3B82F6 vs. brand crimson #9B1B30 + gold #C9A227 focus-only), the rationed status ramp (teal #2DD4BF / amber #E5A84B / coral #E85A6B / sky #60A5FA dark), Figtree weights 400/500/600 only, dark-default, the 4px grid. Signature components (KpiTile with its 3px status stripe + arrow + label, StatusChip dot-not-color-alone, Panel quiet-lift) are built once per platform from these tokens. Pipeline + samples: design-tokens/.

## 9. Earned-urgency notifications

A notification is the most expensive signal Hummingbird can send. The taxonomy is a clinical-safety component with acceptance criteria — a mis-tuned one causes alarm fatigue (staff silence the app and miss the real breach). Four tiers:

| Tier | Meaning | iOS | Android | Quiet hours |
| --- | --- | --- | --- | --- |
| T1 Critical breach | Threshold breach / safety event, act now | Critical Alert (entitlement) | Full-screen intent | Overrides (capped) |
| T2 Actionable | Assigned to you to act on soon | Time-Sensitive + actions | High-importance + actions | Deferred unless STAT |
| T3 Awareness | Worth knowing, not urgent | Passive | Default/low | Silenced |
| T4 Digest | Periodic summary | Scheduled | Scheduled low | Silenced |

Principles

- Severity earned per event (most state changes are GLANCE, silent).

- Route to the person who can act (needs the assignment model).

- The action is in the notification (Approve/Claim/Acknowledge from the lock screen, zero app-open).

- Respect the human (per-tier opt-in, quiet hours, per-shift budget, dedupe/coalesce).

- No PHI ever (generic copy, CI payload linter).

- Escalate, don’t repeat (unacked T1/T2 → re-deliver → next responsible → web command center, fully logged).

The complete event→tier→audience→action taxonomy: reference/05-notifications-earned-urgency.md.

## 10. Security & HIPAA gates

Security is a release gate, not a backlog. The cheapest, highest-impact wins, done first: no PHI in notifications/logs/app-switcher snapshots, biometric-gated token storage + auto-lock, TLS + cert pinning with no PHI on public channels.

Plus: encrypted local cache (SQLCipher), FLAG_SECURE/privacy-view, jailbreak/root + attestation (App Attest/Play Integrity), MDM/remote-wipe, action-level RBAC, tamper-evident audit logging, BAA-covered or PHI-free SDKs only, and WCAG 2.2 AA (status-never-by-color, dynamic type, VoiceOver/TalkBack, 44pt targets). The seven non-negotiable release-gate criteria are in reference/06-security-hipaa.md §9 and are written into the program Definition of Done.

## 11. The shared core every worker gets

Regardless of role/phase, every persona’s app is built from the same primitives — only the feed sources and ranking weights change:

- Secure entry — token login, biometric unlock, auto-lock, forced-change honored.

- Role-aware home — the altitude’s most important truth, glanceable; workflow switcher.

- The “For You” queue — one prioritized, cross-domain list of what needs this worker, ranked by earned-urgency score, each card carrying its primary action inline.

- Rationed, actionable notifications (§9).

- House/unit status glance — role-scoped, PHI-gated; tile + widget + (phased) Live Activity/complication.

- Directory & search — the web’s ⌘K as a search screen.

- Profile/preferences & deep links — default workflow, notification tiers, quiet hours, theme; “Open in Zephyrus” for every WEB-deferred path.

This is why one app spans the porter and the CMO: shared primitives, role-tuned feed.

PART III

# The Phased Plan

Each phase is a self-contained work package: thesis · why now · backend · mobile · features & personas · notifications · exit criteria. All phases assume the Invariants (Part II).

## Phase 0 — Foundation

~6–8 WEEKS  ·  THE UNBLOCK

Thesis

A signed-in worker on both platforms can authenticate with biometrics, hit a secured BFF, receive a push, and see one real RTDC tile. Nothing user-facing ships, but everything after depends on it.

Why now

The three gating gaps (§3) block 100% of features. Building them first is the only rational sequence.

Backend

- Sanctum token auth: HasApiTokens on User; POST /api/auth/token{,/refresh,/revoke} + /auth/change-password — additive, honoring must_change_password. OIDC+PKCE path stubbed.

- mobile_devices registry + push service (APNs .p8 HTTP/2 + FCM v1) behind a PushNotifier contract; queued via Horizon.

- BFF scaffold (/api/mobile/v1/*): uniform envelope, role-scoping, PHI-minimization, /me, /realtime/config, /rtdc/census.

- Assignment model — user_id FKs on owners (today Barrier.owner/RtdcPlan.owner are free-text) + a user_unit pivot. Prerequisite for both the For-You queue and notification routing.

- RBAC Policy layer; remediate the auth-less operational endpoints (a standing security issue regardless of mobile).

Mobile (both platforms)

- Repo + CI scaffold; KMP `shared` skeleton (domain/data/platform); SKIE bridge.

- Design-token pipeline wired (DTCG → Compose/SwiftUI); core-ui primitives (KpiTile, StatusChip, Panel). (Already started — `design-tokens/`.)

- Auth flow: token + biometric unlock + auto-lock + Keychain/Keystore; cert pinning.

- BFF client (Ktor), SQLDelight cache, outbox skeleton, push registration.

Features / personas

None user-facing (foundation).

Notifications

Delivery pipeline stood up; one test push.

Exit criteria Auth regression suite green (locked flow unchanged); a device receives a test push; one live /rtdc/census tile renders on iOS and Android via the BFF; security checklist §1–§3 pass.

## Phase 1 — Frontline workers & bed flow

~6–8 WEEKS  ·  HIGHEST, FASTEST VALUE

Thesis

Transporters and EVS techs run their jobs from the phone; bed managers place beds and clear barriers on the move; everyone gets a working For-You queue and rationed pushes.

Why now

All LIVE endpoints, clean lifecycles, lowest backend risk, and the clearest mobile win (transporter/EVS are mobile users; bed managers want placement off-workstation).

Backend

- BFF: RTDC (/rtdc/census, /house, /bed-requests + /{id}/decision, /barriers + /{id}/resolve), Transport (/queue, /{id}/status|assign|handoff), EVS (/queue, /{id}/status).

- Add `BarrierUpdated` broadcast (barriers don’t broadcast today, unlike census/huddle).

- Server-side evaluators for events with no native trigger: SLA breach (needed_at/at_risk), capacity deficit (bed_need>0, available→0), barrier aging, unplaced bed request. Wire into the notification router v1 (tiers, routing via assignment model, quiet hours, budget).

Mobile

- Transport (P1): claim → run trip (17-status) → structured handoff; STAT push.

- EVS (P2): claim → start (SOP/PPE for isolation) → complete (notifies bed manager).

- RTDC beds & barriers (P3/P5): live unit census + safe capacity (Reverb WS); pending bed requests + transparent placement decision (accept/edit/reject); log/resolve barriers.

- For-You queue v1 across these domains; first widget / Live Activity (active trip; unit/house status glance).

Features / personas

P1 Transporter, P2 EVS, P3 Charge Nurse (beds/barriers), P5 Bed Manager — activated.

Notifications

STAT transport/isolation bed-turn assigned (T1); new pending bed request, unplaced bed, aging barrier, SLA at-risk (T2); bed-turn completed (T3).

Exit criteria A transporter claims a STAT job from the lock screen in < 10 s; a bed manager places a bed from a push; evaluators fire correctly within the per-shift budget.

## Phase 2 — Decisions & the OR board

~8–10 WEEKS  ·  THE MARQUEE OPS-LEADER + OR PHASE

Thesis

Ops leaders approve and assign operational actions on the go; executives get a single quiet strain screen + Brief; OR staff get a live board, case tracking, and safety-note SLAs.

Why now

Ops approvals reuse /api/ops/* verbatim (highest value, near-zero backend), and the OR data/contract already exist (needs only three bug-fixes). This is the decision-making heart of the product.

Backend

- BFF: Ops (/ops/inbox, /approvals/{id}/decision, /actions/{id}/{assign,start,complete}) delegating to OperationalActionLifecycleService; Command Center (/command/house, /brief); OR (/or/board, /cases/today, /cases/{id}, /{id}/status, safety-notes, milestones, transport).

- Fix the OR backend bugs first: ORCaseController@store writes string status not status_id; analytics SQL references non-existent or_cases.actual_start/end_time (route via orlog+case_metrics); reference endpoints filter is_active but the column is active_status.

- Add the huddle action-items API (RtdcPlan table exists with no API/UI today).

Mobile

- Ops approvals (P6): approve/reject/assign/start/complete + agent-inbox glance tiles.

- Command Center / Exec Brief (P9): strain index (0–4), hero KPIs with trust badges, the server-composed brief; sparse exec notifications.

- Perioperative (P4/P7): live room board + my cases + single-case tracking; advance status; safety-note SLA acknowledge; pre-op milestone ack; transport-to-OR.

- RTDC huddles (P3/P6): unit-huddle steps (WS-synced) + huddle action-items.

- Dynamic Island / Live Activity for room board + house strain; iOS Critical Alerts + Android full-screen-intent wired for T1 only (apply for entitlements now — they gate GA).

Features / personas

P4 OR Nurse, P6 Capacity Lead, P7 Periop Manager, P9 Executive — activated; P3 gains huddles.

Notifications

Recommendation awaiting approval, action expiring/overdue, safety-note SLA, pre-op milestone incomplete (T2; Crit safety-note + house-status escalation T1); case delayed, first-case late start, cancellation (T2/T3).

Exit criteria A capacity lead approves an action from a notification; an OR nurse acknowledges an overdue safety note; the exec home is a single quiet strain screen that escalates correctly.

## Phase 3 — Awareness breadth

~6–8 WEEKS

Thesis

The glanceable signals that already exist as data — ED boarding/diversion/surge, staffing gaps — reach the right leaders; at-a-glance coverage extends to watch and widgets.

Why now

These are GLANCE/NOTIFY built on existing computed metrics; they broaden situational awareness without the net-new backend that ED actions and PI need.

Backend

- BFF: ED signals (/ed/signals — boarding, diversion, LWBS, surge from Command/Analytics); Staffing (/staffing/requests, /{id}/status); regional/inter-facility transfer.

- Diversion endpoint + `DiversionUpdated` broadcast (model exists, no API/broadcast today).

- Evaluators: ED boarding band (≥6), ESI 1–2 LWBS, surge; staffing below-minimum-safe.

Mobile

- ED glanceable signals (P9/P5): boarding, diversion, LWBS, surge tiles; ESI 1–2 LWBS as T1.

- Staffing (P10): open requests, below-safe alerts, create/source/assign/fill.

- Watch / Wear complications for house/unit status; widget breadth.

Features / personas

P10 Staffing Coordinator — activated; P5/P9 gain ED awareness.

Notifications

ED diversion active, ESI 1–2 LWBS, unit below minimum-safe (T1); ED boarding band crossing, boarder dwell >4h, surge critical, staffing unfilled/escalated (T2).

Exit criteria ED breaches page the right leaders within budget; a staffing coordinator fills a gap from mobile; glance surfaces cover house status across widgets/watch.

## Phase 4 — Net-new backend features

~8–10 WEEKS  ·  BACKEND-LED

Thesis

The domains that are mock/stub on the web today get real backend, then their mobile-worthy slices.

Why now

These require net-new backend (Process Improvement returns empty stubs; PDSA write routes referenced by the web don’t exist; ED has no clinician write path). Doing them last lets the high-value live-data features ship first and de-risks the net-new work.

Backend

- Build the missing PI/PDSA write paths; ED boarder-dwell evaluator and (if scoped) a net-new ED clinician write path; integration-health alerts (connector-down, dead-letter spike); simulation read (results/promoted recommendations — authoring stays web).

Mobile

- PI/PDSA (P8): cycle ownership + stage advance + barrier ack.

- ED actions: boarder-dwell breaches; live-board/triage acknowledgements if the write path exists.

- Integration health glance + alerts for ops/admin.

Features / personas

P8 PI/Quality Lead — activated; ED gains limited actions.

Notifications

PDSA stage due, barrier assigned (T2); boarder dwell >4h (T2); connector down / dead-letter spike (T2/T3, ops/admin).

Exit criteria PI leads manage PDSA on mobile; ED dwell breaches notify; ops sees feed health.

## Phase 5 — Hardening & GA

~4–6 WEEKS

Thesis

The app passes its safety, security, performance, and accessibility gates and rolls out behind flags.

Work

- Full security + clinical-safety reviews (notification-taxonomy sign-off); penetration test; PHI-leak audit; accessibility audit (WCAG 2.2 AA).

- Performance/battery tuning (WS lifecycle, background sync, BFF payload sizes).

- Offline-edge hardening (409/conflict UX, outbox reconciliation, stale-badge correctness).

- Store readiness (privacy nutrition labels, Critical Alerts entitlement approval, data-safety form); pilot → phased rollout behind feature flags.

Exit criteria All release-gate criteria pass; pilot units validate time-to-act and notification budgets; GA.

PART IV

# Reference

## Appendix A — Full feature-parity matrix

Maps every web data element/function to a mobile treatment, satisfying “map to all data elements and functionality.” GLANCE / ACT / NOTIFY / WEB · backend LIVE / MOCK / NEW / WS · phase. Field-level detail per domain: reference/01-feature-parity-matrix.md and research/.

### RTDC — Real-Time Demand & Capacity (flagship)

| Capability | Treatment | Backend | Phase |
| --- | --- | --- | --- |
| Unit census + acuity-adjusted safe capacity | GLANCE·NOTIFY | LIVE·WS | 1 |
| Hospital bed-need roll-up (net/deficit) | GLANCE·NOTIFY | LIVE·WS | 1 |
| Bed (status/isolation/gender) | GLANCE | LIVE | 1 |
| Bed request — list / create | GLANCE·ACT·NOTIFY | LIVE | 1 |
| Bed placement decision — accept/edit/reject (transparent score) | ACT | LIVE | 1 |
| Barrier to discharge — list / log / resolve | GLANCE·ACT·NOTIFY | LIVE | 1 |
| Huddle (unit/service/global) + steps | GLANCE·ACT | LIVE·WS | 2 |
| Huddle action items (owner/due) | ACT·NOTIFY | NEW | 2 |
| Discharge prediction / reconciliation / GMLOS | GLANCE | LIVE | 2 |
| Care-journey milestone | GLANCE | LIVE | 2 |
| Diversion event | GLANCE·NOTIFY | NEW | 3 |
| Discharge readiness / priorities | GLANCE·ACT | NEW (mock) | 3 |
| RTDC deep analytics / trends | WEB | MOCK | — |

### Perioperative (ready data, greenfield surface)

| Capability | Treatment | Backend | Phase |
| --- | --- | --- | --- |
| OR case (service/surgeon/room/status) | GLANCE·ACT·NOTIFY | LIVE | 2 |
| Wheels clock (ORLog, 13 timestamps) | GLANCE | LIVE | 2 |
| Case status — advance (Sched→InProg→Delay→Comp) | ACT·NOTIFY | LIVE (fix store) | 2 |
| Room status board (derived) | GLANCE·NOTIFY | LIVE | 2 |
| Case timing (progress %/variance) | GLANCE·NOTIFY | LIVE | 2 |
| Safety note — create/ack (SLA 15/30/60/120m) | GLANCE·ACT·NOTIFY | LIVE | 2 |
| Pre-op milestone — ack (H&P/Consent/Labs) | ACT·NOTIFY | LIVE | 2 |
| Case transport — ready/complete | ACT·NOTIFY | LIVE | 2 |
| Provider directory / reference data | GLANCE / lookup | LIVE | 2 |
| Block/primetime/turnover/provider/service analytics; forecasts | WEB | LIVE/MOCK | — |

### Ops / AI & Command Center (“approvals on the go”)

| Capability | Treatment | Backend | Phase |
| --- | --- | --- | --- |
| Recommendation (title/risk/rationale) | GLANCE·NOTIFY | LIVE | 2 |
| Operational action lifecycle (draft→…→completed, expires +8h) | GLANCE·ACT·NOTIFY | LIVE | 2 |
| Approve / reject approval ★ | ACT·NOTIFY | LIVE | 2 |
| Assign / start / complete (override/expire P3) | ACT | LIVE | 2/3 |
| Agent inbox summary | GLANCE | LIVE | 2 |
| House strain/surge index (0–4) + hero KPIs + 24h forecast | GLANCE·NOTIFY | LIVE | 2 |
| Executive Brief (situation/plan/impact/confidence) | GLANCE·NOTIFY | LIVE | 2 |
| Intervention/metric trust/lineage/freshness | GLANCE | LIVE | 3 |
| Data-quality finding (stale feed) | GLANCE·NOTIFY | LIVE | 3 |
| Simulation author / ops graph / process mining | WEB | LIVE | — |

### Emergency Department (glance now, act later)

| Capability | Treatment | Backend | Phase |
| --- | --- | --- | --- |
| ED boarding count (≤6) · LWBS % · door-to-provider/LOS · surge | GLANCE·NOTIFY | LIVE (Command/Analytics) | 3 |
| Active diversion · ESI 1–2 LWBS (safety) | GLANCE·NOTIFY | LIVE/NEW | 3 |
| Boarder dwell >4h since admit decision | NOTIFY | NEW | 4 |
| Live ED board / triage / disposition | ACT | NEW | 4+ |
| ED flow/wait/resource/acuity/arrival analytics | WEB | MOCK | — |

### Transport · EVS · Staffing (mobile workers)

| Capability | Treatment | Backend | Phase |
| --- | --- | --- | --- |
| Transport request + 17-status lifecycle; claim/progress/assign | GLANCE·ACT·NOTIFY | LIVE | 1 |
| Transport structured handoff (to/summary/docs/risks) | ACT·NOTIFY | LIVE | 1 |
| Regional / inter-facility transfer | GLANCE·ACT | LIVE | 3 |
| EVS bed-turn + 5-status; claim/start/complete; isolation SOP | GLANCE·ACT·NOTIFY | LIVE | 1 |
| Staffing plan (gap/min-safe) + request; create/source/assign/fill | GLANCE·ACT·NOTIFY | LIVE | 3 |

### Process Improvement · Patient Flow/FHIR/Integration · Platform

| Capability | Treatment | Backend | Phase |
| --- | --- | --- | --- |
| PDSA cycle (plan/do/study/act) — own/advance; barrier ack | GLANCE·ACT·NOTIFY | NEW | 4 |
| Bottleneck / root-cause / process mining / 4D navigator | WEB | MOCK | — |
| Flow encounter/event/occupancy; patient identity; FHIR; ambient | feeds census/board | LIVE | 1–2 |
| Integration source/health/connector; dead-letter | GLANCE·NOTIFY (admin) | LIVE | 4 |
| Facility blueprint / space modeling | WEB | LIVE | — |
| Auth · biometric · workflow switcher · profile/prefs · search · directory | ACT·GLANCE | LIVE + NEW | 0–2 |
| Admin (users, auth providers) | WEB | LIVE | — |

Coverage assertion Every audited model maps to a row above or its domain’s WEB bucket. The domains carrying the most NEW backend (ED actions, PI/PDSA, RTDC huddle action-items & discharge-readiness) are precisely those that are mock/stub on the web today — net-new product, not a mobile gap — which is why they land in P3–P4.

## Appendix B — Backend change log

Consolidated additive backend work (detail: reference/04-backend-requirements.md):

| Area | Work | Phase |
| --- | --- | --- |
| Auth | HasApiTokens; /auth/token{,/refresh,/revoke}, /auth/change-password (honor must_change_password); OIDC+PKCE path; token abilities | 0 |
| Push | mobile_devices registry; APNs .p8 + FCM v1 PushNotifier; notification router | 0→1 |
| BFF | /api/mobile/v1/* scaffold; per-domain endpoints rolled out P1–P4; uniform envelope; PHI-minimization | 0–4 |
| Assignment/RBAC | user_id FKs on owners + user_unit pivot; Laravel Policies; remediate auth-less endpoints | 0 |
| Broadcasts | BarrierUpdated (P1); DiversionUpdated (P3); WS config endpoint | 1–3 |
| Evaluators | SLA / capacity deficit / barrier aging / unplaced bed (P1); ED boarding/LWBS/surge, staffing min-safe (P3); boarder dwell, integration health (P4) | 1–4 |
| Bug fixes | OR store status_id; analytics actual_start/end_time → orlog/metrics; reference active_status | before 2 |
| Net-new | huddle action-items API (P2); PI/PDSA write paths, ED write path, simulation read (P4) | 2–4 |

## Appendix C — Risk register

| Risk | Sev | Mitigation |
| --- | --- | --- |
| KMP commitment decided late → costly re-architecture | High | Decide now (§5). Floor: separate apps + mandated OpenAPI contract + shared conformance spec |
| Earned-urgency mis-tuned → alarm fatigue or missed breach (safety) | High | Treat taxonomy as clinical-safety; configurable bands; clinical sign-off gate; track T1 precision + per-shift budget |
| PHI leak (notifications/logs/snapshots/SDKs) | High | PHI-free push by design + CI payload linter + FLAG_SECURE/privacy view + BAA/PHI-free SDKs; PHI-leak audit gate |
| Auth additivity breaks the locked flow | High | Strict additive design; auth regression suite as a P0 gate; never touch protected files |
| Net-new backend gates ED/PI slips features | Med | Sequence last (P4); ship glanceable signals first (P3); deep-link-to-web fallback |
| Push reliability on battery-constrained devices | Med | Push-first + delta-sync; never hold a bg socket; poll-on-resume fallback; real-device testing |
| Apple Critical Alerts / Android FSI permission delays | Med | Apply early in P2; degrade T1 to high-importance until granted |
| Web endpoints currently auth-less = security finding | Med | Remediate in P0; BFF is the only mobile surface |
| Reference/OR backend bugs block P2 | Low | Fix list scheduled before P2 (Appendix B) |

## Appendix D — Team & timeline

| Role | Count | Focus |
| --- | --- | --- |
| iOS (Swift/SwiftUI) | 2 | native UI, widgets/Live Activities, watch |
| Android (Kotlin/Compose) | 2 | native UI, Glance widgets, Wear |
| KMP / shared | 1 | domain/data/sync/tokens (pairs with both) |
| Backend (Laravel) | 1–2 | BFF, auth, push, evaluators, RBAC, broadcasts |
| Design | 1 | token parity, mobile component specs, glanceability |
| QA / security | 1 | conformance + security/PHI gates |
| Clinical-safety advisor | part | notification taxonomy + tier sign-off |
| PM / EM | 1 | sequencing, store, rollout |

Timeline: ~9–12 months to GA; internal pilots from end of P1; P1–P2 overlap once the BFF pattern is set.

## Appendix E — Program definition of done

- The parity matrix is fully reconciled: every GLANCE/ACT/NOTIFY row shipped or explicitly deferred with a tracked backend ticket; every WEB row has a working deep link.

- All seven security release-gate criteria pass (reference/06-security-hipaa.md §9), notably: zero PHI leaves the boundary (notifications/logs/snapshots/analytics); auth additivity proven by a green regression suite over the locked flow; biometric + auto-lock + remote-revoke; cert pinning with rotation; action RBAC unbeatable by a tampered client; audit trail on every mutation; named security + clinical-safety sign-off.

- The notification taxonomy meets its precision/budget criteria in pilot and has clinical-safety sign-off.

- One design system, three platforms — verified non-divergent by the token CI check.

## Document map

This consolidated plan is the front door. Detail lives in:

Deep-dive planning docs

- 00 Vision/Scope/Personas · 01 Feature-Parity Matrix · 02 Functionality by Role · 03 Architecture

- 04 Backend & API · 05 Notifications · 06 Security/HIPAA · 07 Roadmap & Phasing

Scaffolding (begun)

- design-tokens/ — DTCG source + Style Dictionary + samples.

- api-contract/hummingbird-bff.v1.yaml — validated OpenAPI 3.1.

Evidence — the seven-stream code audit

research/ (01–07: ED, RTDC, Perioperative, Improvement/Ops, Platform, Supporting domains, Mobile best practices).